## Final
Client | 1.1Challenges in land acquisition | 5 | [4], [8], [9], [29], [38]
| 1.2 Unrealistic contract duration | 24 | [1], [2], [4], [5], [6], [7], [8], [13], [15], [18], [19], [21], [22], [23], [24], [26], [27], [28], [29], [31], [32], [33], [36], [38]
| 1.3 Delay in the decision-making process | 29 | [1], [3], [4], [5], [6], [7], [8], [9], [12], [13], [15], [17], [18], [19], [21], [22], [23], [25], [26], [28], [29], [30], [31], [32], [33], [35], [36], [37], [38]
| 1.4 Financial problems of the client | 15 | [1], [2], [3], [7], [8], [10], [12], [14], [21], [22], [24], [26], [30], [37], [38]
| 1.5 Site handover delays | 13 | [3], [5], [6], [8], [10], [14], [19], [21], [23], [27], [31], [33], [37]
| 1.6 Slow approval of design documents by the client | 8 | [5], [7], [11], [15], [19], [21], [27], [31]
| 1.7 Frequent change orders | 26 | [1], [2], [3], [5], [6], [7], [8], [10], [12], [13], [15], [17], [18], [19], [21], [22], [23], [24], [27], [29], [30], [31], [32], [33], [37], [38]
| 1.8 High rate of changes in client managers | 4 | [2], [23], [29], [37]
| 1.9 Delay in progress payments | 32 | [1], [2], [3], [4], [5], [6], [7], [8], [11], [12], [13], [14], [15], [17], [18], [19], [21], [22], [23], [24], [25], [26], [27], [28], [29], [30], [31], [32], [33], [35], [37], [38]
| 1.10 Unproductive rewards and penalties | 10 | [4], [5], [19], [21], [23], [27], [29], [31], [33], [37]
| 1.11 Interference by the client | 7 | [8], [12], [13], [19], [23], [36], [37], [38]
| 1.12 Unqualified representatives | 5 | [6], [21], [23], [27], [38]
| 1.13 Choosing the lowest-priced contractor | 16 | [1], [2], [3], [5], [6], [7], [8], [9], [10], [11], [16], [23], [29], [36], [37], [38]
| 1.14 Additional tasks | 11 | [20], [22], [23], [24], [25], [27], [29], [30], [33], [36], [38]
Consultant | 2.1 Numerous changes in design | 16 | [2], [7], [9], [14], [15], [17], [21], [22], [23], [24], [26], [27], [28], [30], [33], [34]
| 2.2 Drawings with insufficient details | 17 | [1], [2], [3], [5], [6], [7], [10], [14], [15], [17], [18], [19], [21], [27], [31], [33], [37]
| 2.3 Inadequate preliminary data collection and surveying | 10 | [4], [7], [8], [9], [10], [14], [21], [27], [28], [31]
| 2.4 Incomplete design documents | 6 | [5], [10], [15], [20], [24], [27]
| 2.5 Improper budget forecasts | 10 | [1], [2], [6], [7],[8], [22], [28], [32], [35], [36]
| 2.6 Inexperienced design team | 18 | [1], [2], [3], [5], [6], [8], [10], [14], [15], [19], [20], [21], [23], [27], [31], [32], [37], [38]
| 2.7 Slowness in approving scope changes | 8 | [1], [5], [9], [10], [20], [21], [27], [31]
| 2.8 Inadequate investigation of the site | 10 | [7], [8], [13], [21], [22], [24], [27], [33], [34], [38]
| 2.9 insufficient supervision and inspection | 27 | [1], [5], [6], [8], [9], [10], [12], [13], [14], [15], [17], [18], [19], [21], [22], [23], [25], [27], [28], [29], [30], [31], [33], [35], [36], [37], [38]
| 2.10 Poor contract management | 11 | [2], [6], [10], [12], [13], [23], [28], [32], [35], [37], [38]
| 2.11 Design errors | 17 | [1], [3], [5], [6], [7], [8], [10], [19], [21], [22], [23], [27], [30], [31], [32], [34], [37]
| 2.12 Inability to provide instructions on time | 9 | [1], [6], [15], [18], [20], [23], [25], [26], [38]
| 2.13 Slowness in preparing designs | 16 | [1], [2], [3], [5], [6], [7], [12], [13], [15], [22], [26], [27], [31], [32], [33], [38]
| 2.14 Inconsistencies in contract documents | 18 | [1], [5], [12], [13], [17], [18], [21], [23], [24], [25], [27], [29], [30], [31], [32], [36], [37], [38]
| 20.15 Delay in approving material samples and shop drawings | 18 | [1], [5], [6], [7], [8], [9], [13], [18], [19], [22], [23], [29], [30], [31], [33], [36], [37], [38]
Contractor | 3.1 Recurrent subcontractors changes | 7 | [3], [5], [21], [22], [27], [31], [33]
| 3.2 Inefficient site management and supervision | 32 | [1], [2], [3], [4], [5], [6], [7], [8], [10], [11], [12], [13], [15], [16], [18], [19], [20], [21], [22], [23], [24], [25], [26], [27], [28], [30], [31], [32], [34], [36], [37], [38]
| 3.3 Delay in site mobilization | 8 | [1], [4], [5], [15], [18], [19], [23], [31]
| 3.4 Inadequate experience of the contractor | 25 | [1], [2], [5], [6], [7], [8], [11], [12], [13], [14], [15], [16], [18], [19], [21], [22], [27], [28], [29], [30], [32], [33], [36], [37], [38]
| 3.5 Outdated construction techniques | 15 | [6], [10], [13], [17], [18], [21], [23], [26], [27], [28], [29], [31], [32], [33], [37]
| 3.6 Contractor's financial difficulties | 29 | [1], [2], [3], [4], [5], [6], [8], [10], [12], [13], [14], [15], [16], [17], [18], [19], [20], [22], [23], [24], [26], [28], [30], [31], [32], [33], [35], [37], [38]
| 3.7 lack of proper subcontractor management | 11 | [2], [8], [15], [20], [23], [30], [32], [33], [34], [37], [38]
| 3.8 Rework due to errors | 30 | [1], [2], [3], [4], [5], [8], [12], [13], [14], [15], [18], [19], [20], [21], [22], [24], [25], [26], [27], [28], [29], [30], [31], [32], [33], [34], [35], [36], [37], [38]
| 3.9 Poor project planning and scheduling | 28 | [1], [2], [3], [4], [5], [6], [7], [8], [9], [10], [12], [15], [16], [18], [19], [21], [23], [24], [26], [27], [30], [31], [32], [33], [34], [35], [37], [38]
| 3.10 Unqualified project team | 13 | [2], [3], [6], [10], [15], [18], [21], [23], [24], [27], [31], [37], [38]
| 3.11 Contractor's incapacity to procure imported materials | 3 | [23], [29], [35]
Material | 4.1 Material changes during project execution | 15 | [1], [5], [6], [14], [19], [20], [21], [22], [23], [25], [27], [28], [31], [36], [37]
| 4.2 Delays in material procurement | 25 | [1], [2], [3], [5], [6], [8], [9], [11], [15], [18], [19], [21], [22], [23], [27], [29], [30], [31], [32], [33], [34], [35], [36], [37], [38]
| 4.3 Increase in material prices | 20 | [1], [2], [6], [7], [8], [9], [16], [17], [21], [22], [23], [24], [26], [27], [28], [29], [33], [35], [37], [38]
| 4.4 Material damage | 12 | [3], [5], [8], [21], [22], [23], [24], [27], [28], [31], [33], [37]
| 4.5 Shortages of materials | 24 | [1], [2], [3], [5], [6], [8], [12], [13], [15], [17], [18], [19], [21], [22], [23], [24], [27], [30], [31], [32], [35], [36], [37], [38]
| 4.6 Usage of low-quality materials | 16 | [1], [2], [3], [5], [8], [10], [12], [13], [15], [17], [21], [23], [25], [27], [29], [36]
Labour | 5.1 Inexperienced laborers | 10 | [5], [6], [8], [18], [21], [22], [23], [25], [27], [31]
| 5.2 Lack of qualified workers | 26 | [1], [2], [3], [4], [5], [6], [7], [8], [9], [11], [12], [13], [15], [16], [18], [19], [21], [22], [23], [25], [26], [28], [31], [32], [33], [35]
| 5.3 Absenteeism | 5 | [3], [8], [21], [27], [29]
| 5.4 Low productivity | 16 | [1], [2], [3], [5], [7], [13], [15], [17], [21], [22], [24], [27], [28], [31], [32], [33]
Equipment | 6.1 Inefficient equipment | 14 | [1], [3], [4], [5], [6], [15], [17], [21], [22], [27], [28], [29], [31], [33]
| 6.2 Inadequate or outdated equipment | 15 | [1], [2], [3], [5], [6], [14], [17], [18], [21], [23], [24], [25], [26], [27], [31]
| 6.3 Excessive breakdown of equipment | 13 | [4], [5], [7], [13], [14], [19], [21], [22], [23], [24], [27], [31], [35]
| 6.4 Equipment shortage | 17 | [2], [4], [5], [6], [7], [8], [12], [13], [15], [19], [21], [22], [23], [27], [31], [32], [35]
External | 7.1 Environmental constraints | 4 | [8], [19], [21], [29]
| 7.2 Legislation and regulation changes | 19 | [1], [3], [5], [8], [9], [13], [14], [17], [18], [19], [21], [23], [24], [25], [27], [29], [31], [33], [35]
| 7.3 Force majeure | 13 | [1], [6], [8], [9], [19], [21], [22], [24], [26], [27], [29], [30], [31]
| 7.4 Severe weather condition | 27 | [1], [3], [5], [6], [8], [10], [12], [13], [14], [15], [17], [18], [19], [20], [21], [24], [25], [26], [27], [28], [29], [30], [31], [32], [33], [34], [35]
| 7.5 Inflation | 17 | [2], [3], [6], [8], [9], [10], [12], [14], [17], [19], [21], [24], [25], [26], [27], [28], [31]
| 7.6 Slow process for securing permits from government agencies | 20 | [4], [5], [6], [8], [9], [10], [12], [13], [15], [18], [19], [21], [22], [23], [24], [27], [29], [31], [33], [35]
Project | 8.1 Unforeseen geological conditions | 27 | [1], [3], [4], [5], [6], [7], [8], [9], [12], [13], [17], [18], [19], [20], [21], [23], [24], [25], [27], [28], [30], [31], [33], [34], [35], [37], [38]
| 8.2 Poor communication and coordination | 30 | [1], [3], [5], [6], [7], [8], [9], [12], [13], [14], [15], [17], [18], [19],[20], [21], [22], [23], [25], [27], [28], [29], [30], [31], [32], [33], [34], [36], [37], [38]
| 8.3 Construction accidents | 19 | [1], [5], [6], [8], [13], [14], [15], [17], [18], [19], [21], [23], [24], [25], [27], [28], [29], [30], [33]
| 8.4 Challenges posed by locals | 11 | [1], [3], [4], [5], [13], [19], [21], [27], [32], [36], [37]
| 8.5 Disputes between parties | 14 | [4], [5], [9], [12], [17], [21], [23], [24], [26], [27], [28], [31], [36], [37]

## Initial
Contractor | High number of contracts by same contractor | 4 | [8], [16], [25], [28]
| Low ability of contractor to provide imported material | 3 | [23], [29], [35]
| Inadequate site investigation | 4 | [5], [13], [23], [27]
| Slow preparation of shop drawings and samples of materials | 3 | [1], [6], [19]
| Inadequate contractor experience | 24 | [1], [2], [5], [6], [7], [8], [11], [12], [13], [14], [15], [16], [18], [19], [21], [22], [27], [28], [29], [30], [32], [33], [36], [37], [38]
| The contractor’s financial problems | 28 | [1], [2], [3], [4], [5], [6], [8], [10], [12], [13], [14], [15], [16], [17], [18], [19], [20], [22], [23], [24], [26], [28], [30], [31], [32], [33], [35], [37], [38]
| Ineffective project planning and scheduling | 26 | [1], [2], [3], [4], [5], [6], [7], [8], [9], [10], [12], [15], [16], [18], [19], [21], [23], [24], [26], [27], [30], [31], [32], [33], [34], [35], [37], [38]
| Poor financial control on site | 12 | [2], [6], [10], [12], [15], [21], [23], [27], [28], [29], [30], [35]
| Poor site management and supervision | 21 | [1], [2], [3], [4], [5], [6], [7], [8], [10], [11], [12], [13], [15], [16], [18], [19], [20], [21], [22], [23], [24], [25], [26], [27], [28], [30], [31], [32], [34], [36], [37], [38]
| Rework due to errors during construction | 29 | [1], [2], [3], [4], [5], [8], [12], [13], [14], [15], [18], [19], [20], [21], [22], [24], [25], [26], [27], [28], [29], [30], [31], [32], [33], [34], [35], [36], [37], [38]
| Incompetent project team | 12 | [2], [3], [6], [8], [10], [15], [18], [21], [23], [24], [27], [31], [37], [38]
| Delay in site mobilization | 8 | [1], [4], [5], [15], [18], [19], [23], [31]
| Poor management of subcontractors | 10 | [2], [8], [15], [20], [23], [30], [32], [33], [34], [37], [38]
| Delays in sub-contractors work | 12 | [2], [5], [6], [9], [12], [13], [14], [19], [29], [30], [31], [36]
| Frequent change of subcontractors | 7 | [3], [5], [21], [22], [27], [31], [33]
| Unreliable subcontractors | 9 | [1], [6], [8], [21], [22], [24], [27], [32], [36]
| Inappropriate construction methods | 16 | [2], [6], [10], [13], [17], [18], [21], [23], [26], [27], [28], [29], [31], [32], [33], [37]
Client | Complexity of the project | 4 | [1], [21], [25], [27]
| Inappropriate feasibility study of the project | 4 | [10], [21], [27], [37]
| Inadequate planning | 4 | [5], [9], [10], [27]
| Lack of experience of client's team | 5 | [6], [14], [18], [21], [27]
| Delay in decision making | 29 | [1], [3], [4], [5], [6], [7], [8], [9], [12], [13], [15], [17], [18], [19], [21], [22], [23], [25], [26], [28], [29], [30], [31], [32], [33], [35], [36], [37], [38]
| Frequent change of client managers | 4 | [2], [23], [29], [37]
| Inadequate fund allocation | 6 | [6], [7], [16], [17], [28], [35]
| Slowness in reviewing and approving design documents by owner | 10 | [1], [5], [7], [11], [15], [19], [21], [27], [31], [32]
| Owner interference | 7 | [12], [13], [19], [23], [36], [37], [38]
| Lack of capable representative | 5 | [6], [21], [23], [27], [38]
| Financial difficulties from the client side | 15 | [1], [2], [3], [7], [8], [10], [12], [14], [21], [22], [24], [26], [30], [37], [38]
| Unrealistic contract duration | 24 | [1], [2], [4], [5], [6], [7], [8], [13], [15], [18], [19], [21], [22], [23], [24], [26], [27], [28], [29], [31], [32], [33], [36], [38]
| Ineffective delay penalties | 9 | [4], [5], [19], [21], [23], [27], [29], [31], [37]
| Lack of incentives for contractor to finish ahead of schedule | 8 | [4], [21], [23], [27], [29], [31], [33], [37]
| Wrong budgeting of project sections | 3 | [2], [9], [10]
| Delays in land acquisition | 5 | [4], [8], [9], [29], [38]
| Lowest/unqualified bidder selection | 16 | [1], [2], [3], [5], [6], [7], [8], [9], [10], [11], [16], [23], [29], [36], [37], [38]
| Delay in site delivery | 13 | [3], [5], [6], [8], [10], [14], [19], [21], [23], [27], [31], [33], [37]
| Delay in materials to be supplied by the owner | 3 | [29], [33], [37]
| Delay in progress payments | 32 | [1], [2], [3], [4], [5], [6], [7], [8], [11], [12], [13], [14], [15], [17], [18], [19], [21], [22], [23], [24], [25], [26], [27], [28], [29], [30], [31], [32], [33], [35], [37], [38]
| Frequent change orders by clients | 26 | [1], [2], [3], [5], [6], [7], [8], [10], [12], [13], [15], [17], [18], [19], [21], [22], [23], [24], [27], [29], [30], [31], [32], [33], [37], [38]
| Additional work | 11 | [20], [22], [23], [24], [25], [27], [29], [30], [33], [36], [38]
| Delay in approval of completed work by client | 5 | [22], [30], [33], [35], [37]
| Suspension of work by owner | 5 | [5], [19], [23], [27], [31]
Consultant | Misunderstanding of owner’s requirements | 8 | [1], [5], [7], [14], [21], [27], [31], [37]
| Insufficient data collection and survey before design | 10 | [4], [7], [8], [9], [10], [14], [21], [27], [28], [31]
| Inaccurate site investigation | 9 | [7], [13], [21], [22], [24], [27], [33], [34], [38]
| Lack of experience of the design team | 18 | [1], [2], [3], [5], [6], [8], [10], [14], [15], [19], [20], [21], [23], [27], [31], [32], [37], [38]
| Lack of coordination among design disciplines | 3 | [2], [15], [18]
| Conflicts between consultant and design engineer | 4 | [5], [21], [27], [31]
| Delays in producing design documents | 16 | [1], [2], [3], [5], [6], [7], [12], [13], [15], [22], [26], [27], [31], [32], [33], [38]
| Design errors | 17 | [1], [3], [5], [6], [7], [8], [10], [19], [21], [22], [23], [27], [30], [31], [32], [34], [37]
| conflicts of design drawings details and specifications | 7 | [6], [19], [23], [26], [27], [29], [37]
| Complexity of project design | 6 | [2], [8], [14], [18], [27], [31]
| Incomplete project design | 6 | [5], [10], [15], [20], [24], [27]
| Unclear and inadequate details in drawings | 17 | [1], [2], [3], [5], [6], [7], [10], [14], [15], [17], [18], [19], [21], [27], [31], [33], [37]
| Poor contract management | 11 | [2], [6], [10], [12], [13], [23], [28], [32], [35], [37], [38]
| Design changes | 16 | [2], [7], [9], [14], [15], [17], [21], [22], [23], [24], [26], [27], [28], [30], [33], [34]
| Inaccurate understanding of the contract by the parties | 8 | [2], [14], [17], [21], [23], [27], [31], [36]
| Mistakes and discrepancies in the contract documents | 18 | [1], [5], [12], [13], [17], [18], [21], [23], [24], [25], [27], [29], [30], [31], [32], [36], [37], [38]
| Inadequate budget estimation | 9 | [1], [2], [6], [7], [22], [28], [32], [35], [36]
| Lack of effective project control | 21 | [1], [8], [9], [10], [12], [13], [14], [15], [17], [18], [19], [23], [25], [27], [28], [29], [30], [33], [35], [36], [37]
| Delay in conducting inspection and testing | 14 | [1], [5], [6], [12], [18], [21], [22], [23], [27], [30], [31], [35], [37], [38]
| Delay in approving scope changes | 8 | [1], [5], [9], [10], [20], [21], [27], [31],
| Delay in the approval of the completed project sections | 11 | [2], [6], [8], [9], [12], [18], [21], [30], [35], [36], [38]
| Late approval of shop drawings and material samples | 18 | [1], [5], [6], [7], [8], [9], [13], [18], [19], [22], [23], [29], [30], [31], [33], [36], [37], [38]
| Slow to give instructions | 9 | [1], [6], [15], [18], [20], [23], [25], [26], [38]
Project | Lack of communication between project parties | 24 | [1], [3], [6], [7], [8], [12], [13], [14], [15], [17], [18], [19], [21], [22], [23], [25], [27], [30], [31], [32], [34], [36], [37], [38]
| Lack of coordination among different stakeholders | 17 | [1], [5], [6], [7], [8], [9], [18], [20], [21], [23], [27], [28], [29], [31], [33], [37], [38]
| Legal disputes between project participants | 14 | [4], [5], [9], [12], [17], [21], [23], [24], [26], [27], [28], [31], [36], [37]
| Conflicts between project parties | 9 | [5], [6], [8], [13], [17], [22], [25], [28], [31]
| Restricted access at site | 12 | [6], [9], [16], [19], [21], [23], [24], [25], [27], [28], [33], [34]
| Site accidents due to negligence | 16 | [1], [5], [6], [8], [13], [14], [17], [19], [21], [24], [25], [27], [28], [29], [30], [33]
| Site accidents due to lack of safety measures | 18 | [1], [5], [6], [13], [14], [15], [17], [18], [19], [21], [23], [24], [25], [27], [28], [29], [30], [33]
| Poor/unforeseen site conditions | 16 | [1], [3], [5], [6], [8], [9], [12], [13], [17], [18], [20], [24], [25], [28], [30], [38]
| Unexpected geological conditions | 16 | [4], [5], [7], [8], [9], [17], [19], [21], [23], [27], [28], [31], [33], [34], [35], [37]
| Problems with neighbours | 11 | [1], [3], [4], [5], [13], [19], [21], [27], [32], [36], [37]
Material | Poor material quality | 16 | [1], [2], [3], [5], [8], [10], [12], [13], [15], [17], [21], [23], [25], [27], [29], [36]
| Escalation of material prices | 20 | [1], [2], [6], [7], [8], [9], [16], [17], [21], [22], [23], [24], [26], [27], [28], [29], [33], [35], [37], [38]
| Material shortages | 24 | [1], [2], [3], [5], [6], [8], [12], [13], [15], [17], [18], [19], [21], [22], [23], [24], [27], [30], [31], [32], [35], [36], [37], [38]
| Poor procurement of construction materials | 11 | [3], [6], [9], [18], [21], [22], [27], [31], [33], [35], [36]
| Late delivery of materials | 21 | [1], [2], [5], [6], [8], [11], [15], [19], [21], [22], [23], [27], [29], [30], [31], [32], [33], [34], [35], [37], [38]
| Damage of sorted materials | 12 | [3], [5], [8], [21], [22], [23], [24], [27], [28], [31], [33], [37]
| Changes in the type of materials and specifications during construction | 15 | [1], [5], [6], [14], [19], [20], [21], [22], [23], [25], [27], [28], [31], [36], [37]
Equipment | Escalation of equipment prices | 4 | [6], [8], [9], [16]
| Improper equipment | 11 | [1], [2], [3], [5], [14], [18], [21], [23], [25], [27], [37]
| Slow mobilization of equipment | 11 | [2], [5], [9], [14], [15], [27], [29], [30], [34], [35], [37]
| Shortage of equipment | 20 | [2], [4], [5], [6], [7], [8], [12], [13], [15], [19], [21], [22], [23], [27], [31], [32], [35], [36], [37], [38]
| Low efficiency of equipment | 16 | [1], [3], [4], [5], [6], [15], [17], [21], [22], [27], [28], [29], [31], [33], [36], [37]
| Frequent equipment breakdowns | 15 | [4], [5], [7], [13], [14], [19], [21], [22], [23], [24], [27], [31], [35], [36], [37]
| Inadequate modern equipment | 9 | [5], [6], [17], [21], [24], [26], [27], [31], [37]
Labour | Inadequate skilled labour | 29 | [1], [2], [3], [4], [5], [6], [7], [8], [9], [11], [12], [13], [15], [16], [18], [19], [21], [22], [23], [25], [26], [28], [31], [32], [33], [35], [36], [37], [38]
| Low worker productivity | 18 | [1], [2], [3], [5], [7], [13], [15], [17], [21], [22], [24], [27], [28], [31], [32], [33], [36], [37]
| Personal conflicts among workers | 6 | [5], [15], [21], [27], [29], [31]
| Unqualified/inexperienced workers | 12 | [5], [6], [8], [18], [21], [22], [23], [25], [27], [31], [36], [38]
| Low motivation and morale of labour | 5 | [17], [18], [21], [28], [37]
| Absenteeism | 5 | [3], [8], [21], [27], [29]
| Strike | 7 | [6], [17], [21], [24], [25], [27], [29]
External | Changes in government regulations and laws | 21 | [1], [3], [5], [8], [9], [13], [14], [17], [18], [19], [21], [23], [24], [25], [27], [29], [31], [33], [35], [36], [37]
| Inappropriate government policies | 11 | [1], [6], [14], [17], [22], [26], [27], [30], [32], [33], [38]
| Inflation | 19 | [2], [3], [6], [8], [9], [10], [12], [14], [17], [19], [21], [24], [25], [26], [27], [28], [31], [36], [37]
| Corruption | 5 | [1], [8], [21], [27], [31]
| Economic Problems | 9 | [6], [8], [17], [21], [26], [27], [30], [37], [38]
| Unfavorable weather conditions | 19 | [1], [3], [5], [6], [8], [10], [12], [13], [14], [15], [17], [18], [19], [20], [21], [24], [25], [26], [27], [28], [29], [30], [31], [32], [33], [34], [35], [37], [38]
| Delay in obtaining permits from municipality | 20 | [4], [5], [6], [8], [9], [10], [12], [13], [15], [18], [19], [21], [22], [23], [24], [27], [29], [31], [33], [35]
| Environmental restrictions | 4 | [8], [19], [21], [29]
| Force majeure – war, strikes, bad weather, flood, earth quake, land sliding etc. | 15 | [1], [6], [8], [9], [19], [21], [22], [24], [26], [27], [29], [30], [31], [37], [38]
| Effect of social and cultural factors | 5 | [8], [21], [31], [34], [36]
| Thefts done on site | 3 | [17], [27], [29]
| Unavailability of utilities in site | 6 | [7], [18], [19], [21], [27], [31]
| Delay in performing final inspection and certification by a third party | 4 | [18], [19], [24], [27]
| Bureaucracy in Government agencies | 3 | [6], [23], [31]

## Refrences
Yap, Jeffrey Boon Hui, et al. "Revisiting critical delay factors for construction: Analysing projects in Malaysia." Alexandria Engineering Journal 60.1 (2021): 1717-1729.
Abbasi, Omid, et al. "Exploring the causes of delays in construction industry using a cause-and-effect diagram: Case study for Iran." Journal of Architectural Engineering 26.3 (2020): 05020008.
Yaseen, Zaher Mundher, et al. "Prediction of risk delay in construction projects using a hybrid artificial intelligence model." Sustainability 12.4 (2020): 1514.
Shengea, Noah W., R. N. Misra, and S. K. Mishra. "Construction Delay analysis of some indian Hydropower Projects." Water and Energy International 62.10 (2020): 61-67.
Gondia, Ahmed, et al. "Machine learning algorithms for construction projects delay risk prediction." Journal of Construction Engineering and Management 146.1 (2020): 04019085.
Islam, Muhammad Saiful, and Bambang Trigunarsyah. "Construction delays in developing countries: a review." Journal of Construction Engineering and Project Management 7.1 (2017): 1-12.
Khan, Raza Ali, Uneb Gazder, and Abdul Qayoom. "Comparison of delay factors and remedies’ rankings for building construction projects in developing countries." International Journal of Advanced and Applied Sciences 4.4 (2017): 33-42.
Alamri, Nasser, Omar Amoudi, and Gibril Njie. "Analysis of construction delay causes in dams projects in Oman." European Journal of Business and Social Sciences 6.2 (2017): 19-42.
Batool, Aysha, and Faisal Abbas. "Reasons for delay in selected hydro-power projects in Khyber Pakhtunkhwa (KPK), Pakistan." Renewable and Sustainable Energy Reviews 73 (2017): 196-204.
Samarghandi, Hamed, et al. "Studying the Reasons for Delay and Cost Overrun in Construction Projects: The Case of Iran." (2016).
Alzara, Majed, et al. "Using PIPS to minimize causes of delay in Saudi Arabian construction projects: university case study." Procedia Engineering 145 (2016): 932-939.
Bagaya, Ousseni, and Jinbo Song. "Empirical study of factors influencing schedule delays of public construction projects in Burkina Faso." Journal of Management in Engineering 32.5 (2016): 05016014.
Hisham, Syahira Nabilla Ahmad, and Khairulzan Yahya. "Causes and effects of delays in construction industry." Universiti Teknologi Malaysia (2016).
Kim, Soo-Yong, and Kiet Nguyen Tuan. "Delay factor analysis for hospital projects in Vietnam." KSCE Journal of Civil Engineering 20.2 (2016): 519-529.
Asadi, Ahmad, Mohammed Alsubaey, and Charalampos Makatsoris. "A machine learning approach for predicting delays in construction logistics." International Journal of Advanced Logistics 4.2 (2015): 115-130.
Islam, Mohammad Saiful, et al. "Causes of delay in construction projects in Bangladesh." The 6th International Conference on Construction Engineering and Project Management, Busan, Korea. 2015.
Amoatey, Charles Teye, et al. "Analysing delay causes and effects in Ghanaian state housing construction projects." International Journal of Managing Projects in Business (2015).
Jarkas, Abdulaziz M., and Jamal H. Younes. "Principle factors contributing to construction delays in the State of Qatar." International Journal of Construction Project Management 6.1 (2014): 39.
Marzouk, Mohamed M., and Tarek I. El-Rasas. "Analyzing delay causes in Egyptian construction projects." Journal of advanced research 5.1 (2014): 49-55.
Mydin, MA Othuman, et al. "Imperative causes of delays in construction projects from developers’ outlook." MATEC Web of Conferences. Vol. 10. EDP Sciences, 2014.
Muhwezi, L., J. Acai, and G. Otim. "An assessment of the factors causing delays on building construction projects in Uganda." International journal of construction engineering and management 3.1 (2014): 13-23.
Rahman, M. D., Young Dai Lee, and Duy Khanh Ha. "Investigating main causes for schedule delay in construction projects in Bangladesh." Journal of Construction Engineering and Project Management 4.3 (2014): 33-46.
Shehu, Zayyana, Intan R. Endut, and Akintola Akintoye. "Factors contributing to project time and hence cost overrun in the Malaysian construction industry." Journal of Financial Management of Property and Construction (2014).
Choudhry, Rafiq M., et al. "Cost and schedule risk analysis of bridge construction in Pakistan: Establishing risk guidelines." Journal of Construction Engineering and Management 140.7 (2014): 04014020.
Alinaitwe, Henry, Ruth Apolot, and Dan Tindiwensi. "Investigation into the causes of delays and cost overruns in Uganda's public sector construction projects." Journal of Construction in Developing Countries 18.2 (2013): 33.
Gardezi, S. Shujaa Safdar, Irfan Anjum Manarvi, and S. Jamal Safdar Gardezi. "Time extension factors in construction industry of Pakistan." Procedia Engineering 77 (2014): 196-204.
Aziz, Remon Fayek. "Ranking of delay factors in construction projects after Egyptian revolution." Alexandria Engineering Journal 52.3 (2013): 387-406.
Kazaz, Aynur, Serdar Ulubeyli, and Nihan Avcioglu Tuncbilekli. "Causes of delays in construction projects in Turkey." Journal of civil Engineering and Management 18.3 (2012): 426-435.
Fallahnejad, Mohammad Hossein. "Delay causes in Iran gas pipeline projects." International Journal of project management 31.1 (2013): 136-146.
Mohammed, Kasimu Alhaji, and Abubakar Danladi Isah. "Causes of delay in Nigeria construction industry." Interdisciplinary journal of contemporary research in business 4.2 (2012): 785-794.
Niazai, Ghulam Abbas, and Kassim Gidado. "Causes of project delay in the construction industry in Afghanistan." Proceedings of the EPPM (2012).
Pourrostam, Towhid, and Amiruddin Ismail. "Causes and effects of delay in Iranian construction projects." International Journal of Engineering and Technology 4.5 (2012): 598.
Doloi, Hemanta, et al. "Analysing factors affecting delays in Indian construction projects." International journal of project management 30.4 (2012): 479-489.
Orangi, A., E. Palaneeswaran, and J. Wilson. "Exploring delays in Victoria-based Astralian pipeline projects." Procedia engineering 14 (2011): 874-881.
Ejaz, Naeem, Imran Ali, and Muhammad Fiaz Tahir. "Assessment of delays and cost overruns during construction projects in Pakistan." (2011).
Abbasnejad, Behzad, and H. Izadi Moud. "Construction delays in Iranian civil engineering projects: An approach to the financial security of construction business." Life Science Journal 10.2 (2013): 2632-2637.
Kazemi, Aliyeh, Eun-Seok Kim, and Mohammad-Hossein Kazemi. "Identifying and prioritizing delay factors in Iran’s oil construction projects." International Journal of Energy Sector Management (2020).
Kog, Yue Choong. "Major delay factors for construction projects in Iran." International Journal of Construction Project Management 9.2 (2017): 83-97.