## dataset
| 1.1Challenges in land acquisition | 1.2 unrealistic contract duration | 1.3 Delay in the decision-making process | 1.4 Financial problems of the client | 1.5 Site handover delays | 1.6 Slow approval of design documents by the client | 1.7 Frequent change orders | 1.8 High rate of changes in client managers | 1.9 Delay in progress payments | 1.10 Unproductive rewards and penalties | 1.11 Interference by the client | 1.12 Unqualified representatives | 1.13 Choosing the lowest-priced contractor | 1.14 Additional tasks | 2.1 Numerous changes in design | 2.2 Drawings with insufficient details | 2.3 Inadequate preliminary data collection and surveying | 2.4 Incomplete design documents | 2.5 Improper budget forecasts | 2.6 Inexperienced design team | 2.7 Slowness in approving scope changes | 2.8 Inadequate investigation of the site | 2.9 insufficient supervision and inspection | 2.10 Poor contract management | 2.11 Design errors | 2.12 Inability to provide instructions on time | 2.13 Slowness in preparing designs | 2.14 Inconsistencies in contract documents | 20.15 Delay in approving material samples and shop drawings | 3.1 Recurrent subcontractors changes | 3.2 Inefficient site management and supervision | 3.3 Delay in site mobilization | 3.4 Inadequate experience of the contractor | 3.5 Outdated construction techniques | 3.6 Contractor's financial difficulties | 3.7 lack of proper subcontractor management | 3.8 Rework due to errors | 3.9 Poor project planning and scheduling | 3.10 Unqualified project team | 3.11 Contractor's incapacity to procure imported materials | 4.1 Material changes during project execution | 4.2 Delays in material procurement | 4.3 Increase in material prices | 4.4 Material damage | 4.5 Shortages of materials | 4.6 Usage of low-quality materials | 5.1 Inexperienced laborers | 5.2 Lack of qualified workers | 5.3 Absenteeism | 5.4 Low productivity | 6.1 Inefficient equipment | 6.2 Inadequate or outdated equipment | 6.3 Excessive breakdown of equipment | 6.4 Equipment shortage | 7.1 Environmental constraints | 7.2 Legislation and regulation changes | 7.3 Force majeure | 7.4 Severe weather condition | 7.5 Inflation | 7.6 Slow process for securing permits from government agencies | 8.1 Unforeseen geological conditions | 8.2 Poor communication and coordination | 8.3 Construction accidents | 8.4 Challenges posed by locals | 8.5 Disputes between parties |  |  | label
Project 1 | 15.8889 | 14.6667 | 16 | 23.3333 | 14.6667 | 14.4444 | 11.5556 | 10 | 16 | 17.3333 | 7.7778 | 8 | 12 | 7.7778 | 13.3333 | 10.6667 | 12 | 8.8889 | 7.7778 | 10 | 9 | 10.1111 | 5.4444 | 6.2222 | 7.7778 | 8.8889 | 8.5556 | 7 | 11.1111 | 16 | 12 | 7.7778 | 10 | 9.7778 | 21.7778 | 10.6667 | 8 | 12 | 10 | 9.7778 | 10.6667 | 13.3333 | 8.6667 | 8.8889 | 13 | 7 | 5.3333 | 8 | 7 | 9 | 9 | 11.1111 | 13.3333 | 13.3333 | 11 | 11 | 8 | 10.6667 | 23.3333 | 13.3333 | 10.6667 | 6.1111 | 8.8889 | 18.6667 | 12 | 0 | 84 | 2
Project 2 | 9.3333 | 10 | 11.5556 | 25 | 7.3333 | 14 | 8 | 8.5556 | 17.1111 | 4.4444 | 6 | 6.1111 | 7.7778 | 11 | 14.6667 | 9.7778 | 14.6667 | 13.4444 | 6.6667 | 9.3333 | 7.7778 | 9.3333 | 7.3333 | 8.6667 | 6.2222 | 10.8889 | 7 | 7.7778 | 9.3333 | 12 | 6.6667 | 6 | 4.6667 | 9.3333 | 8 | 10.6667 | 8.6667 | 11.5556 | 6.6667 | 4.4444 | 15.8889 | 12.2222 | 12.2222 | 7.3333 | 21.6667 | 4.8889 | 5 | 7.2222 | 5.3333 | 8.6667 | 11.5556 | 8.6667 | 13 | 17.3333 | 10 | 14.6667 | 9.3333 | 13 | 25 | 20 | 15 | 5 | 9.7778 | 2.6667 | 5 | 1 | 36 | 2
Project 3 | 17.3333 | 9.3333 | 5.5556 | 20.2222 | 8 | 7.7778 | 8 | 3.8889 | 18.7778 | 4.6667 | 7.3333 | 6.6667 | 5.5556 | 6 | 5.5556 | 6.2222 | 9.7778 | 8.8889 | 10.1111 | 6.6667 | 7.7778 | 7.7778 | 5.5556 | 5.5556 | 8.5556 | 6.6667 | 6.6667 | 6.6667 | 7.7778 | 6 | 8 | 6.6667 | 7.7778 | 5 | 9.3333 | 9.3333 | 10.1111 | 6.6667 | 8 | 4.4444 | 3.1111 | 8 | 20.2222 | 5.5556 | 12 | 6.2222 | 6.2222 | 7.7778 | 7.7778 | 7.7778 | 5.5556 | 4.4444 | 7 | 10 | 10 | 6.6667 | 8 | 15.8889 | 21.7778 | 14.6667 | 13.3333 | 4.4444 | 8.8889 | 21.7778 | 7 | 1 | 36 | 0
Project 4 | 18.7778 | 20.2222 | 9.3333 | 17.3333 | 10 | 13 | 8.6667 | 7.3333 | 16 | 12.2222 | 10.6667 | 6.6667 | 15.5556 | 7.3333 | 8 | 7.3333 | 9.3333 | 7.3333 | 12.2222 | 8.5556 | 5.3333 | 8 | 6.1111 | 6 | 8.6667 | 6 | 6 | 6.6667 | 6.6667 | 9 | 9.3333 | 7 | 8.5556 | 11 | 16 | 11 | 6 | 11.5556 | 8 | 9.7778 | 9.7778 | 11 | 14.6667 | 7.3333 | 13.3333 | 7.1111 | 7 | 6.6667 | 7 | 8 | 9.7778 | 12.2222 | 9 | 12 | 9 | 8.5556 | 6.6667 | 8.5556 | 25 | 10.6667 | 9.7778 | 8.5556 | 8 | 11.5556 | 14.6667 | 1 | 48 | 1
Project 5 | 9.3333 | 4 | 4 | 13 | 8 | 4 | 8 | 2.6667 | 10.6667 | 2 | 6 | 4 | 4 | 6 | 3.3333 | 4 | 5.3333 | 4 | 5 | 6.6667 | 4 | 4 | 4.6667 | 4 | 5 | 6.6667 | 6.6667 | 4 | 4 | 4 | 5.3333 | 4 | 6.6667 | 4 | 5.3333 | 5.3333 | 5 | 4 | 5 | 9.3333 | 4 | 8 | 25 | 4 | 12 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 12 | 20 | 9.3333 | 8 | 6.6667 | 25 | 25 | 9.3333 | 16 | 4 | 8 | 16 | 3 | 1 | 60 | 0
Project 6 | 20.2222 | 20.2222 | 10.6667 | 25 | 13.3333 | 14.4444 | 9.3333 | 8.5556 | 18.7778 | 18.6667 | 8.5556 | 10.6667 | 13 | 9.3333 | 12 | 10.6667 | 10.6667 | 9.7778 | 8.8889 | 13.3333 | 8 | 10.8889 | 7.7778 | 7.7778 | 10.1111 | 8.8889 | 8.8889 | 7 | 10 | 16 | 12 | 4.4444 | 10.6667 | 12.2222 | 25 | 9.3333 | 7 | 14 | 7 | 13 | 12 | 10.6667 | 10.8889 | 9.7778 | 13.3333 | 8 | 5.3333 | 11.1111 | 8 | 10 | 10 | 13.4444 | 10.6667 | 14.6667 | 6.6667 | 10 | 10.6667 | 9.3333 | 25 | 13.3333 | 12 | 7.7778 | 10 | 15.8889 | 13.3333 | 0 | 18 | 2
Project 7 | 21.7778 | 18.7778 | 10 | 21.7778 | 14.6667 | 7 | 10.6667 | 8.8889 | 18.7778 | 9 | 13 | 8.8889 | 8 | 8.5556 | 9.3333 | 5.3333 | 10.1111 | 8.8889 | 6.6667 | 6.6667 | 8.5556 | 5.3333 | 4.4444 | 7.2222 | 9.7778 | 9.3333 | 11.1111 | 6.1111 | 7.3333 | 7 | 12.2222 | 6.2222 | 9.3333 | 7.7778 | 21.7778 | 7.1111 | 6.2222 | 10.1111 | 11 | 5.5556 | 5 | 9.7778 | 15.8889 | 7 | 13.4444 | 8 | 8 | 8.8889 | 11 | 6.6667 | 7.3333 | 8.5556 | 7.7778 | 6.6667 | 14.6667 | 11 | 9.3333 | 8.5556 | 21.7778 | 13.3333 | 9.7778 | 5.5556 | 7.3333 | 13.4444 | 7.7778 | 1 | 108 | 2
Project 8 | 14.6667 | 10 | 12.2222 | 18.6667 | 11.1111 | 8.5556 | 13.3333 | 6.6667 | 15.8889 | 10 | 6.6667 | 7.1111 | 6.6667 | 8.5556 | 13.3333 | 5.5556 | 10.8889 | 6.6667 | 5.5556 | 7.7778 | 8.5556 | 9.3333 | 4 | 10.8889 | 8.5556 | 11.5556 | 10.6667 | 6.6667 | 12 | 8.8889 | 14 | 11 | 8.8889 | 6.1111 | 17.3333 | 9.7778 | 7.7778 | 8.8889 | 10.6667 | 6.6667 | 7.3333 | 11.5556 | 12.2222 | 8 | 14 | 9.7778 | 8 | 4.4444 | 7.7778 | 8.5556 | 7.7778 | 8.5556 | 10 | 8.6667 | 15.5556 | 8.5556 | 10.1111 | 10.6667 | 23.3333 | 12 | 10.6667 | 5.3333 | 7.3333 | 15.5556 | 7.7778 | 1 | 60 | 1
Project 9 | 18.6667 | 23.3333 | 13.4444 | 20.2222 | 14.4444 | 17.1111 | 12.4444 | 13.4444 | 13.3333 | 21.7778 | 11.5556 | 8 | 15.8889 | 6.6667 | 14.4444 | 9.7778 | 13 | 8.8889 | 9 | 10.6667 | 7 | 9.3333 | 5.4444 | 6.6667 | 7.7778 | 6.6667 | 6.6667 | 6.2222 | 8 | 17.3333 | 15.5556 | 6.2222 | 8.8889 | 14.4444 | 23.3333 | 8 | 8.8889 | 14.4444 | 10 | 7.7778 | 12 | 12.2222 | 6.6667 | 9 | 9.7778 | 6.2222 | 5.3333 | 8 | 6.2222 | 10 | 13.4444 | 13.4444 | 7.7778 | 9.7778 | 8 | 9 | 10.6667 | 7.2222 | 23.3333 | 12.2222 | 7.3333 | 7.7778 | 11 | 10.6667 | 17.3333 | 0 | 84 | 2
Project 10 | 16 | 16.6667 | 11 | 21.7778 | 13.4444 | 8.5556 | 9.3333 | 5.4444 | 15.8889 | 12.2222 | 11.5556 | 9.7778 | 10.1111 | 5.4444 | 5.5556 | 8.5556 | 8 | 10.6667 | 9.7778 | 10 | 8 | 7.3333 | 5.3333 | 4.6667 | 10.1111 | 6.2222 | 13 | 7.7778 | 11.1111 | 11.1111 | 12 | 7.7778 | 13 | 7.1111 | 23.3333 | 8.5556 | 7.7778 | 6.6667 | 10 | 13 | 3.5556 | 12.4444 | 15.8889 | 8.5556 | 9.3333 | 8 | 6.2222 | 7 | 7 | 9 | 6.6667 | 6.2222 | 12.2222 | 13.3333 | 12 | 8.5556 | 8.6667 | 16 | 18.7778 | 9 | 13.3333 | 9.7778 | 12 | 23.3333 | 13.3333 | 0 | 24 | 1
Project 11 | 10.6667 | 6.1111 | 12 | 14.4444 | 8.5556 | 11.6667 | 9.3333 | 7.1111 | 10.6667 | 9 | 5.3333 | 4 | 10.6667 | 6 | 8.8889 | 8 | 7 | 7.3333 | 10.1111 | 10.6667 | 6.1111 | 10.6667 | 6.6667 | 5.3333 | 4 | 9.7778 | 6.1111 | 6 | 7.3333 | 9.7778 | 6.1111 | 5.7778 | 6 | 7.3333 | 11.5556 | 10.8889 | 11.6667 | 9.7778 | 6.6667 | 12 | 9.3333 | 12 | 14 | 7.3333 | 14.4444 | 6.1111 | 3 | 3.3333 | 5.5556 | 7.7778 | 8.5556 | 8.8889 | 11.1111 | 18.3333 | 7.7778 | 11 | 8 | 21.7778 | 20.2222 | 12 | 16 | 5.5556 | 8.8889 | 15.8889 | 8 | 1 | 18 | 0
Project 12 | 21.7778 | 18.6667 | 10 | 17.1111 | 20.2222 | 9.3333 | 10.8889 | 12.2222 | 17.3333 | 13.3333 | 14.4444 | 10 | 14 | 7.3333 | 7.3333 | 6.6667 | 9.3333 | 10.6667 | 6 | 8 | 8 | 6.2222 | 6.2222 | 6.1111 | 12 | 8.8889 | 12.2222 | 6.6667 | 8 | 11.1111 | 16 | 8 | 13 | 6.6667 | 25 | 4.4444 | 8 | 10.1111 | 13.4444 | 13 | 6.1111 | 13 | 11 | 7.3333 | 7.7778 | 11 | 6.2222 | 9.7778 | 9 | 8 | 7.3333 | 10 | 13.4444 | 11.1111 | 12.2222 | 6.6667 | 9.3333 | 10.6667 | 21.7778 | 8 | 10 | 7.3333 | 10.6667 | 20.2222 | 11 | 0 | 48 | 1
Project 13 | 10.1111 | 5.5556 | 9.7778 | 21.6667 | 6.2222 | 8.5556 | 10.8889 | 4.4444 | 15.8889 | 8 | 8 | 6 | 4.4444 | 6.2222 | 9.7778 | 7 | 13.4444 | 11 | 9.3333 | 7.3333 | 9.7778 | 11.5556 | 2.6667 | 6 | 7.7778 | 7 | 10.1111 | 6.2222 | 9 | 10 | 15 | 9.3333 | 11 | 4.4444 | 10.6667 | 10.6667 | 13 | 8.5556 | 10.6667 | 3.8889 | 4.6667 | 8.5556 | 17.1111 | 7.3333 | 13.3333 | 7 | 7 | 9.7778 | 5.3333 | 7.7778 | 7.7778 | 6 | 6.6667 | 12.2222 | 11.1111 | 10.6667 | 10.6667 | 17.1111 | 20.2222 | 13.3333 | 12 | 3.3333 | 8 | 23.3333 | 5.3333 | 1 | 72 | 0
Project 14 | 20 | 20.2222 | 13.3333 | 14.4444 | 17.3333 | 11.5556 | 9.3333 | 6 | 13.3333 | 17.3333 | 8.5556 | 6 | 15.8889 | 6.1111 | 6.6667 | 7.3333 | 6.6667 | 4.8889 | 10 | 11.5556 | 5.3333 | 5.7778 | 6.6667 | 3.1111 | 10.1111 | 8.8889 | 7 | 4.4444 | 8.8889 | 12.2222 | 10 | 6.2222 | 10.6667 | 11 | 23.3333 | 8.5556 | 5.3333 | 10.6667 | 11 | 12.4444 | 9.3333 | 10.6667 | 8.8889 | 5.5556 | 7.3333 | 8.5556 | 4.6667 | 7.7778 | 6.2222 | 7.3333 | 7 | 12.2222 | 13.3333 | 9.7778 | 8.8889 | 6.6667 | 8 | 6.6667 | 20 | 6.1111 | 11 | 7 | 11 | 18.6667 | 14.6667 | 1 | 120 | 2
Project 15 | 10.6667 | 14.6667 | 12 | 21.6667 | 10.6667 | 20.2222 | 9.7778 | 8.8889 | 17.3333 | 9.7778 | 6.6667 | 9.3333 | 13.4444 | 10 | 14.6667 | 10.1111 | 13.3333 | 8.8889 | 10 | 13.3333 | 8 | 11 | 12 | 7 | 7.3333 | 7.3333 | 7 | 7.1111 | 8.5556 | 14.4444 | 8 | 4.4444 | 5.3333 | 14.4444 | 12.2222 | 10.8889 | 11.5556 | 17.1111 | 8.5556 | 6.2222 | 18.7778 | 11.1111 | 9.3333 | 8.5556 | 16 | 3.5556 | 5 | 10.6667 | 5.5556 | 8.5556 | 12 | 15.8889 | 11.5556 | 17.3333 | 6.2222 | 14.6667 | 10.6667 | 14 | 21.6667 | 18.6667 | 14 | 7 | 11 | 6.1111 | 8.5556 | 0 | 36 | 2
Project 16 | 7.7778 | 6.1111 | 7.3333 | 18.6667 | 8.5556 | 9.3333 | 11.1111 | 8.8889 | 15.8889 | 3.1111 | 7 | 8.5556 | 5.5556 | 11 | 10 | 8.5556 | 11.5556 | 12.2222 | 10 | 10.1111 | 10.6667 | 8.6667 | 7.7778 | 9.3333 | 8 | 15 | 9.7778 | 7.3333 | 9.3333 | 10.6667 | 7.7778 | 7.3333 | 7.1111 | 7.2222 | 7.3333 | 6.6667 | 10 | 7.2222 | 5.7778 | 6.2222 | 13 | 12.2222 | 14.6667 | 7.3333 | 18.7778 | 6.6667 | 6.6667 | 6.6667 | 7.2222 | 8 | 9.3333 | 8.6667 | 14 | 17.3333 | 11 | 12.2222 | 9.7778 | 21.7778 | 23.3333 | 17.3333 | 18.6667 | 6.6667 | 9.3333 | 8 | 4 | 0 | 60 | 0
Project 17 | 7.7778 | 6 | 10.6667 | 17.3333 | 7.7778 | 9.3333 | 9 | 6.2222 | 10 | 3.8889 | 8 | 5.3333 | 5 | 10 | 12.2222 | 8 | 10.6667 | 7.7778 | 8.6667 | 6.1111 | 8.8889 | 9.3333 | 8.6667 | 7.2222 | 4.8889 | 9.3333 | 8.8889 | 8.8889 | 8 | 5.5556 | 7.2222 | 7.2222 | 7 | 6.6667 | 8 | 8 | 10.1111 | 9.7778 | 9.3333 | 5 | 10.6667 | 11.1111 | 20.2222 | 8.8889 | 18.7778 | 5.5556 | 8 | 6.6667 | 4 | 6.6667 | 9.3333 | 5.7778 | 11.1111 | 15.8889 | 10 | 13.3333 | 9.7778 | 21.7778 | 23.3333 | 15.8889 | 16 | 6.1111 | 12.4444 | 7 | 4.4444 | 0 | 48 | 0
Project 18 | 6.6667 | 10.6667 | 10.8889 | 15.8889 | 8 | 13 | 9 | 5.3333 | 12 | 4.6667 | 9 | 6 | 10 | 10 | 9 | 11.5556 | 9.7778 | 11 | 8 | 9.3333 | 8 | 10.6667 | 10.6667 | 8.5556 | 5.3333 | 7.7778 | 6.6667 | 6 | 8.5556 | 14.6667 | 8.5556 | 7.3333 | 8.8889 | 11.5556 | 6.1111 | 9.3333 | 10.8889 | 9.3333 | 8.6667 | 7 | 13.4444 | 10 | 14.6667 | 7.3333 | 20.2222 | 6.1111 | 6 | 4.8889 | 4.4444 | 10.1111 | 9.7778 | 7.3333 | 15.8889 | 18.7778 | 9 | 9 | 9.3333 | 17.3333 | 20.2222 | 14.4444 | 15.8889 | 6.1111 | 8.5556 | 8.5556 | 4.4444 | 0 | 24 | 0
Project 19 | 12 | 12.2222 | 7.3333 | 17.3333 | 9.7778 | 9.7778 | 12 | 9.7778 | 18.7778 | 6.6667 | 13.3333 | 8.6667 | 10.6667 | 11 | 10.1111 | 8 | 13 | 13.3333 | 7.3333 | 6.6667 | 10.6667 | 11.5556 | 5.3333 | 11.6667 | 8.6667 | 11.5556 | 10 | 9.3333 | 8.6667 | 9.7778 | 10.6667 | 7.7778 | 8.5556 | 9.3333 | 11 | 10 | 8.5556 | 10.8889 | 10.1111 | 4.6667 | 12.2222 | 8.8889 | 17.1111 | 7.7778 | 17.1111 | 7.3333 | 8.5556 | 11.5556 | 6.6667 | 5.3333 | 9.3333 | 7.2222 | 11.5556 | 13.3333 | 11.1111 | 11 | 9.3333 | 14.4444 | 18.6667 | 15.8889 | 12 | 8.8889 | 7.3333 | 5 | 9.3333 | 0 | 60 | 2
Project 20 | 10.6667 | 12 | 8 | 17.3333 | 7.3333 | 8.5556 | 8 | 6.1111 | 13.3333 | 3.8889 | 7.7778 | 7.3333 | 9.7778 | 7 | 9.7778 | 5.5556 | 11 | 7.3333 | 7.3333 | 7.3333 | 7.7778 | 8.5556 | 7.2222 | 6.1111 | 7.2222 | 6.1111 | 6 | 5.5556 | 4.8889 | 8 | 7.7778 | 4 | 6 | 9.7778 | 9 | 6.6667 | 7.3333 | 10.6667 | 6.6667 | 4.6667 | 13.3333 | 9 | 12.2222 | 6.6667 | 18.6667 | 6.6667 | 8.8889 | 7.2222 | 6.1111 | 7.2222 | 11.5556 | 10.6667 | 11 | 13 | 5.4444 | 10 | 5.5556 | 11 | 17.3333 | 13 | 12.4444 | 6.6667 | 8 | 3 | 7.7778 | 0 | 24 | 0
Project 21 | 8.5556 | 14.6667 | 16 | 18.7778 | 12 | 15.8889 | 10 | 11 | 17.3333 | 11 | 11.1111 | 6.2222 | 12.2222 | 10 | 17.3333 | 12 | 14.4444 | 12.2222 | 5.3333 | 10 | 8.8889 | 11.5556 | 6.2222 | 8.8889 | 7.3333 | 10.6667 | 8 | 4.6667 | 13.3333 | 15.8889 | 9.7778 | 7.1111 | 6 | 11.1111 | 13.4444 | 13.3333 | 6.2222 | 13.3333 | 8 | 4.4444 | 20.2222 | 12.2222 | 6 | 12 | 13.3333 | 6 | 5.3333 | 6.1111 | 5 | 5.5556 | 10 | 12 | 14 | 17.1111 | 7.1111 | 13.3333 | 11.5556 | 10.6667 | 20.2222 | 13.3333 | 11.5556 | 8.5556 | 9.7778 | 5 | 7.7778 | 1 | 72 | 2
Project 22 | 25 | 25 | 13 | 25 | 15.8889 | 14.6667 | 10 | 12.2222 | 23.3333 | 16 | 9.3333 | 8.5556 | 20.2222 | 7.3333 | 11.5556 | 8.8889 | 10.8889 | 12.2222 | 11 | 6.6667 | 7 | 10.6667 | 6.6667 | 5 | 8.5556 | 7 | 7 | 7.1111 | 7 | 14.4444 | 10.6667 | 3.3333 | 7.7778 | 14.6667 | 25 | 13 | 10 | 10.8889 | 8.8889 | 5.5556 | 8.5556 | 13 | 8.8889 | 9.3333 | 13.4444 | 7.7778 | 5.3333 | 8.8889 | 7.7778 | 8.8889 | 10.1111 | 13.4444 | 11.1111 | 12 | 6.2222 | 7.1111 | 9.3333 | 8 | 20.2222 | 12.2222 | 9.3333 | 6.2222 | 8 | 14 | 15.8889 | 0 | 84 | 2
Project 23 | 12.2222 | 10.6667 | 6.6667 | 17.3333 | 9 | 13.3333 | 6 | 6.6667 | 14.6667 | 11 | 7.1111 | 7.3333 | 13 | 8 | 7.7778 | 11.5556 | 8.8889 | 9.7778 | 8.8889 | 8.8889 | 6.2222 | 8.8889 | 7.7778 | 5.5556 | 8.5556 | 7.7778 | 5.5556 | 5 | 9.3333 | 8.5556 | 7.3333 | 6.2222 | 8 | 12.2222 | 10.6667 | 8.5556 | 10.6667 | 9.7778 | 6 | 8.8889 | 10 | 11 | 14.6667 | 8 | 11 | 7 | 5.4444 | 7.3333 | 8.5556 | 9.7778 | 9.7778 | 8.8889 | 11.1111 | 16 | 7.1111 | 9 | 9.7778 | 13.3333 | 23.3333 | 12 | 14.6667 | 6 | 12.2222 | 14.6667 | 11 | 1 | 24 | 0
Project 24 | 14.4444 | 11 | 6.6667 | 21.6667 | 12.2222 | 8 | 11 | 8.8889 | 18.7778 | 6 | 9.7778 | 11 | 6.6667 | 8.8889 | 8.5556 | 7.1111 | 11 | 10 | 6.6667 | 9.7778 | 13.3333 | 10.1111 | 5.5556 | 8.6667 | 12 | 6.1111 | 13.3333 | 8.5556 | 8.8889 | 8.8889 | 11 | 6.2222 | 8.8889 | 8.5556 | 14.6667 | 8 | 10.6667 | 8 | 13 | 7 | 5.3333 | 9.3333 | 17.3333 | 6.2222 | 13.4444 | 8.8889 | 8 | 10 | 10 | 8 | 8 | 5.3333 | 10.6667 | 11.1111 | 13.3333 | 10 | 9.7778 | 16 | 17.3333 | 12 | 13.3333 | 6.6667 | 10.6667 | 15.8889 | 5 | 0 | 48 | 1
Project 25 | 8.8889 | 9.3333 | 14.4444 | 18.7778 | 9.3333 | 11.5556 | 8.6667 | 6 | 13.4444 | 10 | 4.4444 | 7.3333 | 11.5556 | 10.6667 | 8.5556 | 8.5556 | 9.7778 | 8.5556 | 8.5556 | 11.5556 | 8 | 12.4444 | 8.8889 | 4.6667 | 7.2222 | 6.6667 | 7.2222 | 6.6667 | 8.8889 | 14.4444 | 8 | 6.6667 | 9 | 5.5556 | 13 | 11.5556 | 11.5556 | 11.5556 | 6.6667 | 9 | 7.7778 | 9.7778 | 11.5556 | 4.8889 | 12.4444 | 8.5556 | 7.7778 | 5.5556 | 3.5556 | 11 | 7 | 8.8889 | 12 | 16 | 7 | 9.7778 | 8 | 14.6667 | 23.3333 | 13.4444 | 12 | 5.5556 | 10 | 18.6667 | 10.6667 | 0 | 18 | 0
Project 26 | 17.3333 | 18.6667 | 5.5556 | 20.2222 | 11 | 8.8889 | 8.6667 | 6 | 17.3333 | 10 | 11 | 8 | 13.4444 | 4 | 4 | 8.8889 | 6.6667 | 9.3333 | 12 | 11 | 6.6667 | 6.1111 | 6.1111 | 4.4444 | 10.1111 | 6.2222 | 8.8889 | 3 | 7.1111 | 8 | 8 | 4.6667 | 11 | 8.8889 | 21.7778 | 7.3333 | 7 | 6.6667 | 9.7778 | 14.6667 | 4.4444 | 9.7778 | 11 | 4.4444 | 8 | 8 | 5.4444 | 10 | 8.8889 | 8 | 7.3333 | 8.8889 | 10 | 11 | 7.7778 | 6.6667 | 8.5556 | 12.2222 | 15.8889 | 9 | 13.4444 | 7.1111 | 8 | 21.6667 | 10 | 1 | 72 | 1
Project 27 | 14 | 14.6667 | 12.4444 | 23.3333 | 9.7778 | 13 | 14 | 11 | 21.7778 | 9.3333 | 10.1111 | 9.3333 | 9.7778 | 12 | 15.8889 | 10 | 17.3333 | 9 | 7.3333 | 13 | 10 | 13 | 4 | 12.4444 | 8 | 10.1111 | 6 | 6.6667 | 9.3333 | 13.3333 | 10.6667 | 9.7778 | 7.7778 | 9.3333 | 14.4444 | 14 | 11.5556 | 14 | 10.6667 | 1.3333 | 13.4444 | 12 | 13.4444 | 9.7778 | 20 | 6.6667 | 6 | 12.4444 | 9.3333 | 8 | 10.8889 | 8.5556 | 7.2222 | 9.3333 | 9 | 13.3333 | 8 | 11 | 23.3333 | 18.7778 | 9.3333 | 6.6667 | 9.7778 | 9.3333 | 9.7778 | 0 | 24 | 2
Project 28 | 18.7778 | 15.8889 | 4.4444 | 11.5556 | 7.7778 | 7.7778 | 13 | 6.6667 | 17.3333 | 4.6667 | 10.1111 | 6 | 9.3333 | 8 | 5.5556 | 8.5556 | 9.3333 | 7.3333 | 14.4444 | 8.5556 | 7 | 9.7778 | 10.1111 | 6.6667 | 11.5556 | 6.6667 | 7 | 6.6667 | 6.6667 | 4.4444 | 6.1111 | 5 | 9.3333 | 7.7778 | 8.5556 | 8 | 8.6667 | 6.6667 | 7.2222 | 7.7778 | 5 | 9.7778 | 15.8889 | 7.3333 | 12.2222 | 6.2222 | 5.3333 | 7.3333 | 9.7778 | 8.6667 | 8.5556 | 7.3333 | 9 | 10.6667 | 8 | 8 | 6.1111 | 10 | 20 | 12.2222 | 14.6667 | 10 | 8.5556 | 12.2222 | 9.7778 | 0 | 72 | 0
Project 29 | 8.8889 | 6.6667 | 7.2222 | 12 | 6.1111 | 5.3333 | 7.7778 | 5 | 8.8889 | 3.8889 | 6 | 6.6667 | 3.6667 | 7.7778 | 4.8889 | 6.6667 | 8.6667 | 6.6667 | 9.3333 | 7.2222 | 5.5556 | 6.6667 | 5.7778 | 6.6667 | 7.7778 | 5.5556 | 6.6667 | 6.6667 | 7.2222 | 3.8889 | 8 | 7.2222 | 9.3333 | 5.7778 | 5.3333 | 9.3333 | 6.2222 | 5.7778 | 9.3333 | 9.7778 | 5.3333 | 7.3333 | 25 | 6.1111 | 13 | 6.6667 | 7.3333 | 5.3333 | 6.1111 | 4.8889 | 6.1111 | 6.1111 | 10 | 17.1111 | 12 | 8.6667 | 7.3333 | 23.3333 | 23.3333 | 8.5556 | 14.6667 | 10 | 8 | 14.6667 | 5 | 0 | 48 | 0
Project 30 | 14.6667 | 11.1111 | 6.1111 | 20 | 8.8889 | 9.7778 | 7.7778 | 5.3333 | 12.2222 | 6.2222 | 9.7778 | 6.6667 | 12 | 8.5556 | 7.3333 | 6.6667 | 7.3333 | 4.4444 | 7.7778 | 6 | 4.6667 | 8 | 4.4444 | 5.5556 | 8.5556 | 8.8889 | 8.8889 | 5.3333 | 8 | 8 | 8.5556 | 6 | 8.5556 | 8 | 14.6667 | 10 | 6.2222 | 10.6667 | 9.7778 | 7.7778 | 8 | 7.7778 | 11 | 7.3333 | 12 | 8 | 7 | 7 | 7 | 11.5556 | 8.8889 | 6.2222 | 9 | 12 | 8 | 7 | 5.5556 | 7.7778 | 23.3333 | 8.5556 | 9.7778 | 7.7778 | 4.6667 | 12 | 9.7778 | 0 | 96 | 1
Project 31 | 12 | 18.7778 | 14 | 21.6667 | 11.5556 | 13 | 11 | 10.6667 | 15.8889 | 10.6667 | 8 | 6 | 15.5556 | 13.3333 | 15.8889 | 11 | 16 | 7.7778 | 10 | 9.3333 | 8.8889 | 10.1111 | 7.3333 | 8 | 9.7778 | 9.7778 | 8 | 10 | 9.3333 | 15.8889 | 10.6667 | 7 | 6.2222 | 14.6667 | 14.6667 | 12 | 6.6667 | 15.5556 | 8.5556 | 7 | 20.2222 | 12.2222 | 10 | 9.7778 | 18.7778 | 3.5556 | 6.6667 | 15.5556 | 5.5556 | 8 | 12.2222 | 15.8889 | 12 | 15.5556 | 7.1111 | 13.3333 | 8.5556 | 10.1111 | 21.6667 | 14.4444 | 9.3333 | 9.3333 | 7.1111 | 4.4444 | 12.2222 | 1 | 36 | 2
Project 32 | 10 | 18.7778 | 15.5556 | 17.3333 | 7.7778 | 13.3333 | 8 | 8 | 13.4444 | 13.4444 | 9.7778 | 4.8889 | 18.6667 | 8 | 8 | 7.3333 | 11 | 6.1111 | 12.2222 | 10.1111 | 7 | 10.6667 | 10.6667 | 4.4444 | 5.3333 | 6.6667 | 6.6667 | 6 | 9.7778 | 11.1111 | 8.5556 | 8.5556 | 8 | 9.3333 | 13.4444 | 12 | 5 | 9.7778 | 7.7778 | 10 | 13.3333 | 13 | 11 | 6.1111 | 10.6667 | 7.7778 | 8.8889 | 5.5556 | 4.4444 | 8.6667 | 9.7778 | 12.2222 | 12.2222 | 14.4444 | 6.2222 | 10 | 6.2222 | 10.1111 | 25 | 9.3333 | 10.1111 | 10.6667 | 8 | 10.1111 | 10.6667 | 1 | 120 | 2
Project 33 | 15.8889 | 21.6667 | 12.4444 | 20 | 12.2222 | 17.1111 | 10.8889 | 9.3333 | 18.7778 | 17.3333 | 8.5556 | 9.7778 | 20 | 10.1111 | 14 | 8.5556 | 8 | 10.6667 | 10 | 12 | 5 | 6.6667 | 6.1111 | 6 | 8.6667 | 9.3333 | 9 | 5.5556 | 7.7778 | 13.4444 | 9 | 4.6667 | 9.7778 | 16 | 18.7778 | 9.7778 | 5.3333 | 13 | 7.1111 | 12.2222 | 14.6667 | 13.4444 | 11 | 8.5556 | 12.2222 | 4.4444 | 5 | 8.8889 | 7 | 8.5556 | 11.6667 | 16 | 13.3333 | 15.5556 | 9 | 10 | 8.5556 | 4.4444 | 23.3333 | 9.3333 | 10.6667 | 9.3333 | 11 | 6.1111 | 15.8889 | 0 | 72 | 2
Project 34 | 9.3333 | 10 | 12.4444 | 23.3333 | 8.5556 | 9.7778 | 8.8889 | 8.8889 | 17.3333 | 6.2222 | 7 | 6.6667 | 5.5556 | 12.2222 | 14.6667 | 7 | 14.4444 | 7.7778 | 7.7778 | 7.3333 | 10 | 13 | 6.6667 | 9.3333 | 6.6667 | 6.6667 | 9.3333 | 10.6667 | 9.7778 | 9.7778 | 10.6667 | 6.6667 | 6.2222 | 10.1111 | 11 | 13 | 8 | 13 | 12.4444 | 1.3333 | 14.6667 | 10.6667 | 16 | 6 | 21.6667 | 6 | 11.1111 | 7.7778 | 5.3333 | 10.1111 | 12 | 8 | 9.3333 | 13.3333 | 8.8889 | 14.6667 | 10.1111 | 12 | 21.7778 | 17.1111 | 10.8889 | 3.3333 | 7.7778 | 5.5556 | 9 | 0 | 36 | 2
Project 35 | 10 | 11 | 4.8889 | 14.6667 | 8.8889 | 6.6667 | 8 | 4.4444 | 14.6667 | 4.6667 | 7.7778 | 5.3333 | 11 | 7.1111 | 5 | 5.5556 | 7.3333 | 5.3333 | 11.5556 | 11.5556 | 6.1111 | 6.1111 | 8 | 6.1111 | 7.2222 | 6.6667 | 7 | 4.4444 | 6.1111 | 8 | 6.6667 | 6 | 7.3333 | 8.5556 | 9.7778 | 8 | 7.3333 | 5.3333 | 6.6667 | 8 | 8 | 10 | 21.7778 | 6 | 13.4444 | 8 | 7.7778 | 4.4444 | 6 | 6.1111 | 6.6667 | 8.8889 | 8.8889 | 15.8889 | 7 | 10 | 6.6667 | 17.3333 | 23.3333 | 11 | 13.4444 | 11 | 7.7778 | 12.2222 | 8 | 1 | 18 | 0
Project 36 | 8.5556 | 6.6667 | 5.7778 | 17.3333 | 7 | 9.3333 | 10 | 6.2222 | 16 | 3.3333 | 8 | 7.3333 | 6 | 7.7778 | 7.1111 | 7.7778 | 11 | 9.7778 | 11.5556 | 9.3333 | 7.3333 | 6.1111 | 10.6667 | 11.6667 | 8.6667 | 7.3333 | 8 | 7.3333 | 4.8889 | 5 | 7.2222 | 7.3333 | 8 | 7.2222 | 5.5556 | 8.5556 | 8.6667 | 10.6667 | 7.7778 | 3.3333 | 8.5556 | 10 | 21.6667 | 7.3333 | 20.2222 | 3.3333 | 8 | 10.1111 | 7.2222 | 6.1111 | 9.3333 | 6.1111 | 6.1111 | 14.6667 | 8 | 14.6667 | 10.1111 | 21.7778 | 23.3333 | 18.6667 | 17.1111 | 5.3333 | 9.3333 | 8.8889 | 3.5556 | 1 | 60 | 0
Project 37 | 11.5556 | 4.8889 | 9.7778 | 20 | 8.8889 | 8 | 10.6667 | 3.8889 | 14.6667 | 3.8889 | 8.8889 | 9.7778 | 4.8889 | 7 | 6.2222 | 5.3333 | 9.3333 | 8 | 8 | 6 | 10.6667 | 7.3333 | 9.3333 | 6.6667 | 10.1111 | 11.5556 | 9.3333 | 7.3333 | 10.6667 | 6 | 7.7778 | 8 | 8.8889 | 4.4444 | 7.3333 | 9.3333 | 10.8889 | 8.6667 | 9.3333 | 8.8889 | 8.5556 | 9.3333 | 18.7778 | 7.3333 | 13 | 7.7778 | 7 | 5.5556 | 9.7778 | 9.7778 | 7.3333 | 5 | 12.2222 | 16 | 12 | 13 | 9.7778 | 18.7778 | 23.3333 | 12.2222 | 16 | 7.3333 | 9.3333 | 20.2222 | 5.5556 | 0 | 24 | 0
Project 38 | 6.6667 | 13 | 7.3333 | 18.7778 | 14.6667 | 5 | 11 | 8 | 13 | 5.4444 | 8.8889 | 5.5556 | 8.5556 | 9 | 7.3333 | 4.4444 | 10.6667 | 4 | 6.1111 | 6.6667 | 5.5556 | 4 | 6.6667 | 8 | 8.6667 | 9.3333 | 11.1111 | 6.6667 | 6.6667 | 7.7778 | 13.4444 | 3.8889 | 9.7778 | 7.7778 | 16 | 7.1111 | 6 | 9.3333 | 7.3333 | 5.3333 | 9.3333 | 11 | 14.6667 | 5.3333 | 17.3333 | 7 | 6.6667 | 6 | 7.3333 | 6 | 4.8889 | 9.3333 | 11.5556 | 17.3333 | 13.3333 | 10 | 10.6667 | 10.6667 | 21.6667 | 8.8889 | 11 | 6.1111 | 8 | 10 | 7.3333 | 1 | 48 | 1
Project 39 | 13.3333 | 7.3333 | 9.3333 | 14.6667 | 8 | 4 | 10 | 4.6667 | 8.8889 | 5.3333 | 7.7778 | 5.3333 | 5.5556 | 8 | 7.3333 | 7.3333 | 8.5556 | 5 | 12.4444 | 7.2222 | 4.4444 | 5.5556 | 8 | 6.1111 | 9.3333 | 7.7778 | 6.6667 | 5.3333 | 8 | 4.6667 | 6.6667 | 7.2222 | 8 | 4.8889 | 11 | 8 | 5.7778 | 8.5556 | 10.1111 | 10 | 8.5556 | 9.7778 | 23.3333 | 7.3333 | 13.3333 | 8.5556 | 7.7778 | 6.1111 | 6.6667 | 6.6667 | 6.6667 | 7.7778 | 11.1111 | 12 | 8.5556 | 10.6667 | 7.7778 | 20 | 25 | 12 | 14.6667 | 8 | 12 | 16 | 7.1111 | 0 | 18 | 0
Project 40 | 11 | 6.1111 | 4.8889 | 15.8889 | 7 | 4.4444 | 7 | 5 | 14.6667 | 1.3333 | 6 | 6.1111 | 5.5556 | 8 | 3.5556 | 6 | 10.6667 | 6.6667 | 5.7778 | 7 | 8.5556 | 7.3333 | 8.6667 | 7.3333 | 6.6667 | 8.8889 | 8.8889 | 7.7778 | 5.5556 | 6.2222 | 8 | 6.6667 | 7.7778 | 6 | 6.1111 | 6.6667 | 9.3333 | 6.6667 | 8.6667 | 7.1111 | 5.3333 | 8.5556 | 21.6667 | 4.4444 | 13.4444 | 6.6667 | 8.8889 | 6.1111 | 7.3333 | 4.8889 | 5.5556 | 4.8889 | 10 | 14.6667 | 10 | 9.7778 | 6.6667 | 20.2222 | 20.2222 | 12.2222 | 16 | 6.2222 | 9.7778 | 14.6667 | 6.6667 | 1 | 18 | 0
Project 41 | 18.7778 | 20 | 12 | 18.6667 | 18.7778 | 13.3333 | 10 | 8.5556 | 13 | 14.6667 | 10.6667 | 8.5556 | 18.6667 | 6.1111 | 8.6667 | 10.6667 | 6.6667 | 6.6667 | 6.6667 | 13.3333 | 4 | 5.5556 | 8 | 5.4444 | 6.6667 | 8.8889 | 7 | 6 | 10 | 12.2222 | 8 | 3.5556 | 10.6667 | 11 | 25 | 8.5556 | 4.6667 | 12.4444 | 7 | 15.5556 | 7.7778 | 13.3333 | 7.3333 | 7.3333 | 8.8889 | 11.1111 | 6.2222 | 6.2222 | 8 | 8 | 8.8889 | 12.2222 | 12 | 10 | 8.8889 | 6 | 9.3333 | 8 | 21.6667 | 7.7778 | 10 | 8 | 8.8889 | 20.2222 | 12 | 1 | 24 | 1
Project 42 | 17.1111 | 18.6667 | 9.7778 | 14 | 14.6667 | 7.7778 | 7.2222 | 8.8889 | 12.4444 | 11 | 8.5556 | 8.5556 | 14.6667 | 4 | 4.8889 | 7.7778 | 4.8889 | 4 | 7.3333 | 7 | 6.6667 | 5.5556 | 6.6667 | 4.4444 | 7.2222 | 6.2222 | 7.7778 | 6.6667 | 4.6667 | 9 | 13 | 6 | 9.3333 | 8 | 17.3333 | 6.6667 | 9 | 6.6667 | 7.7778 | 10.1111 | 3.5556 | 13 | 11.1111 | 7.3333 | 4.6667 | 10 | 4.6667 | 7.1111 | 7.7778 | 6.2222 | 5.5556 | 4.6667 | 9.7778 | 8.8889 | 8 | 3.1111 | 10.6667 | 7.3333 | 18.6667 | 6 | 12.2222 | 8.8889 | 8 | 17.3333 | 13.3333 | 0 | 72 | 1
Project 43 | 11.1111 | 14.6667 | 10.1111 | 20.2222 | 7.7778 | 14.4444 | 6.6667 | 6.6667 | 18.7778 | 7.7778 | 5.5556 | 8 | 14.4444 | 5.5556 | 6.6667 | 8.8889 | 11.5556 | 9.7778 | 9.7778 | 12 | 5.5556 | 7.2222 | 7 | 6.6667 | 7.2222 | 7.3333 | 6.6667 | 4 | 7.3333 | 12.2222 | 7.3333 | 5 | 9.7778 | 10.6667 | 11.5556 | 7.7778 | 6.6667 | 7.2222 | 4.4444 | 8.8889 | 7 | 8.8889 | 11.5556 | 4.8889 | 11 | 7 | 4.4444 | 6.6667 | 5.5556 | 7 | 7.7778 | 7 | 9.7778 | 7.3333 | 5.5556 | 9.3333 | 7.3333 | 12 | 23.3333 | 12 | 9 | 5.3333 | 11 | 14.4444 | 8.8889 | 0 | 60 | 0
Project 44 | 10.6667 | 12 | 10.6667 | 14.4444 | 13 | 8 | 8.6667 | 5.5556 | 13 | 8.8889 | 7 | 10.1111 | 11.5556 | 7.7778 | 9.7778 | 7.7778 | 8.5556 | 7.2222 | 6.6667 | 13.3333 | 6 | 5 | 8 | 6.6667 | 4.3333 | 8.8889 | 8.8889 | 5.3333 | 6 | 14.6667 | 9.3333 | 4.4444 | 8.5556 | 6.6667 | 20.2222 | 8.5556 | 3.5556 | 10.6667 | 7.3333 | 13.3333 | 11.5556 | 13 | 12.4444 | 5.5556 | 14.4444 | 4.4444 | 4.4444 | 8 | 6.6667 | 8 | 9.7778 | 13.3333 | 14.4444 | 20.2222 | 6.6667 | 10 | 11.5556 | 14 | 20.2222 | 11.5556 | 14 | 7.3333 | 6.6667 | 10 | 7.3333 | 0 | 48 | 0
Project 45 | 12 | 14.4444 | 15.8889 | 25 | 7.7778 | 15.5556 | 9.7778 | 12.2222 | 20.2222 | 17.1111 | 6.6667 | 8 | 10.6667 | 11.5556 | 14.4444 | 9 | 11 | 11.1111 | 6.2222 | 9.7778 | 8 | 10.6667 | 5.3333 | 5.5556 | 8.8889 | 7.7778 | 8 | 6 | 11.1111 | 13.3333 | 12 | 4.4444 | 6.6667 | 10.6667 | 18.7778 | 12 | 7.7778 | 12 | 7.7778 | 4.4444 | 17.3333 | 8.8889 | 7 | 7.7778 | 13.3333 | 7 | 6.2222 | 11 | 5.3333 | 11 | 12.2222 | 12.2222 | 11.5556 | 9.3333 | 8.5556 | 11.1111 | 7.3333 | 5.5556 | 21.6667 | 13 | 8 | 6 | 6.2222 | 4.4444 | 11 | 0 | 48 | 2
Project 46 | 12.2222 | 12 | 8 | 14.6667 | 10.6667 | 7.7778 | 10.6667 | 4.4444 | 13.4444 | 6.2222 | 9.7778 | 5.5556 | 6.6667 | 5.3333 | 7.7778 | 8 | 8.6667 | 7.7778 | 11.5556 | 10.1111 | 7.3333 | 4.8889 | 8 | 10.1111 | 6.6667 | 9.7778 | 7 | 7.3333 | 6.1111 | 8 | 8 | 6.6667 | 6.6667 | 7.7778 | 13.3333 | 8 | 7.3333 | 8.5556 | 7.2222 | 9.7778 | 6.6667 | 9.7778 | 18.6667 | 6.6667 | 11.1111 | 7.7778 | 7.3333 | 7.3333 | 8.8889 | 5.5556 | 8.5556 | 8.5556 | 9.7778 | 13.4444 | 7.1111 | 7.1111 | 9.3333 | 15.8889 | 21.7778 | 12 | 17.3333 | 8 | 11 | 13.3333 | 6.2222 | 1 | 96 | 0
Project 47 | 21.7778 | 15.5556 | 5.3333 | 17.3333 | 12.2222 | 6 | 8 | 9 | 15.8889 | 6 | 13 | 9.7778 | 9.3333 | 7 | 4 | 6.2222 | 8 | 7 | 10.1111 | 7 | 6.6667 | 4.8889 | 5.5556 | 6.1111 | 8.8889 | 7 | 13.3333 | 5.5556 | 5 | 7.7778 | 11.5556 | 8.5556 | 11.5556 | 8.5556 | 17.1111 | 9.7778 | 7.7778 | 9.3333 | 9.7778 | 10.8889 | 2 | 10.6667 | 17.1111 | 5.5556 | 10 | 9.7778 | 8 | 7.7778 | 7 | 8 | 5.5556 | 4.6667 | 6.2222 | 7.7778 | 12.2222 | 5.5556 | 7.3333 | 12.2222 | 20.2222 | 10 | 12.2222 | 8 | 9.7778 | 17.1111 | 8 | 0 | 84 | 1
Project 48 | 17.3333 | 10.6667 | 7.7778 | 21.7778 | 10 | 5.5556 | 14 | 8 | 17.3333 | 6.6667 | 11 | 8.8889 | 6.6667 | 8 | 6.6667 | 5.3333 | 9.3333 | 10 | 7.7778 | 8.5556 | 11 | 8.5556 | 9.3333 | 11.5556 | 11 | 8.5556 | 12.2222 | 7.3333 | 9.7778 | 8 | 13.3333 | 6.6667 | 10 | 5 | 12.2222 | 8.8889 | 12.2222 | 9.3333 | 10.6667 | 6 | 5.5556 | 10.6667 | 17.3333 | 7 | 12.2222 | 10 | 8.5556 | 11 | 11.1111 | 11 | 7.7778 | 5.3333 | 7.3333 | 8.8889 | 14.6667 | 10.1111 | 10.6667 | 16 | 20.2222 | 15.8889 | 13.4444 | 4.8889 | 10 | 17.1111 | 7.7778 | 0 | 108 | 2
Project 49 | 23.3333 | 21.6667 | 11.5556 | 23.3333 | 15.8889 | 12.2222 | 11 | 12 | 18.7778 | 17.3333 | 11.5556 | 11 | 15.8889 | 8 | 10.8889 | 7.7778 | 10.1111 | 8.8889 | 8.8889 | 8.8889 | 5 | 7.2222 | 7.7778 | 11 | 7 | 10 | 10 | 8.8889 | 12.2222 | 11 | 11 | 3.8889 | 7.2222 | 11 | 23.3333 | 9 | 8 | 13 | 7 | 6.6667 | 11 | 12.2222 | 7 | 9.7778 | 11.1111 | 8 | 7.1111 | 8.8889 | 7.7778 | 10 | 11 | 13.3333 | 8.8889 | 4.4444 | 8 | 8.8889 | 9.7778 | 5.5556 | 18.3333 | 13.3333 | 11.5556 | 8 | 6.6667 | 8.8889 | 12.2222 | 0 | 36 | 2
Project 50 | 20 | 20 | 7 | 18.6667 | 16 | 7.1111 | 10.8889 | 9.3333 | 16.6667 | 12.2222 | 7.7778 | 5.5556 | 8.6667 | 8 | 8.5556 | 6.6667 | 7.2222 | 7.3333 | 8.6667 | 6.6667 | 8 | 9.3333 | 6.6667 | 8.5556 | 8.6667 | 9.3333 | 13.3333 | 8 | 6.1111 | 5 | 12 | 6.1111 | 11.5556 | 9.7778 | 20 | 9 | 8 | 9.3333 | 9.3333 | 10.8889 | 3.8889 | 12 | 14 | 7.7778 | 10 | 12.2222 | 10 | 9 | 10 | 6.6667 | 6.6667 | 8 | 8 | 7.7778 | 14.4444 | 7.3333 | 10.6667 | 8.8889 | 20 | 9.7778 | 13.3333 | 9.7778 | 8 | 14.6667 | 9.7778 | 1 | 24 | 1
Project 51 | 14.6667 | 13.3333 | 12 | 15.5556 | 10 | 6.1111 | 10.1111 | 7.1111 | 13.3333 | 6.2222 | 13 | 8 | 7.2222 | 8.8889 | 7.3333 | 4.6667 | 9.3333 | 6.6667 | 7.3333 | 5.5556 | 8.5556 | 6.2222 | 5.5556 | 8 | 6.6667 | 7.3333 | 8 | 6.1111 | 7.3333 | 6.2222 | 14 | 9.7778 | 9.3333 | 6.6667 | 14.4444 | 8.8889 | 5 | 9.3333 | 12 | 4.4444 | 5 | 9.3333 | 18.3333 | 7.7778 | 12.2222 | 8 | 7 | 5 | 6.6667 | 6.1111 | 9.3333 | 7.7778 | 8.5556 | 8.5556 | 12.2222 | 11.5556 | 8 | 8.8889 | 25 | 11 | 8.5556 | 6.6667 | 6 | 12 | 9.3333 | 1 | 36 | 1
Project 52 | 15.8889 | 13.4444 | 10.6667 | 17.3333 | 13.4444 | 8.5556 | 11.1111 | 6.6667 | 16 | 9 | 11.1111 | 6 | 10.6667 | 8 | 12 | 8 | 6.6667 | 4.4444 | 8 | 6.6667 | 6.6667 | 6.1111 | 4.8889 | 8.6667 | 9.3333 | 12 | 10 | 5.5556 | 8.5556 | 7 | 12 | 5.5556 | 8.5556 | 9.7778 | 17.3333 | 8 | 8 | 12 | 9.3333 | 12 | 6.6667 | 13.4444 | 18.7778 | 9.7778 | 14.6667 | 8.8889 | 6.1111 | 8.5556 | 10.6667 | 7.3333 | 8.5556 | 10.6667 | 13.3333 | 12 | 12 | 10 | 11 | 13.3333 | 23.3333 | 12 | 14.6667 | 8 | 10.6667 | 10 | 6.2222 | 0 | 48 | 1
Project 53 | 14.4444 | 8.8889 | 14.4444 | 25 | 11 | 9.3333 | 11 | 7 | 18.7778 | 7.3333 | 7.3333 | 8.5556 | 6.6667 | 10.6667 | 14.6667 | 5.3333 | 9.3333 | 9.7778 | 5.7778 | 9.3333 | 7.3333 | 10.6667 | 6.1111 | 7.7778 | 7.7778 | 7.2222 | 10 | 7.3333 | 9.3333 | 8.5556 | 12 | 5.5556 | 8 | 7.3333 | 14.6667 | 8 | 9.7778 | 11.5556 | 11.5556 | 3.1111 | 10 | 11 | 13.3333 | 7.7778 | 17.3333 | 5 | 8.8889 | 8.5556 | 8.5556 | 12 | 8.5556 | 8 | 12.4444 | 9.3333 | 13.4444 | 12 | 9.7778 | 12.4444 | 20.2222 | 15.8889 | 11.5556 | 3.6667 | 7.3333 | 8.8889 | 5.5556 | 1 | 60 | 2